## ACTIONS
GRETTON PARISH COUNCIL ACTION PLAN (2014)
SURVEY TOPIC | GOAL(S) | ACTION(S) | ORIGINAL TARGET DATE | REVISED TARGET DATE | STATUS | STATUS DATE | COMMENTS
HOUSING | Influence planning decisions by Tewkesbury Borough Council in respect of size, location and nature of developments. We hope to be able to influence any planning applications, prior to the adoption of the JCS in 2015 and thereafter | Write to TBC Planning Department to make them aware of GPC's views following the 2014 survey | 2014-09-01 | _ | COMPLETE | 2014-09-11 | Letter sent to TBC. (11/09/2014)
ROADS | Improve road conditions | Compile list of damaged roads in Gretton and engage Roger Wilson (Glos County Councillor) to help prioritise repairs | 2014-09-01 | 2015-04-01 | COMPLETE | 12/03/2015 14/04/2015 | Joint survey to be undertaken by PM & PA Survey completed - only 1 issue found
|  | Publish list on web site for comment | 2014-09-01 | 2015-04-01 | CLOSED | 2015-05-14 | The 1 pothole has now been repaired.
|  | Instigate repairs to loose drains and manhole covers | 2014-08-01 | _ | COMPLETE | 2014-08-08 | Drain by Gretton Garage and cover by Village Hall now refitted
| Reduce speeding through Gretton | Obtain and install mobile speed sign to be used at all village approaches. | 2014-09-01 | 2015-01-01 | COMPLETE | 11/09/2014 Jan-2015 | Speed sign purchased and delivered. Posts to be erected (11/09/14). Speed sign now working
|  | Investigate the process for the introduction of traffic calming measures, and white lines on Gopshill bend. | _ | 2015-03-01 | COMPLETE | 2015-03-12 | White lines are not to be recommended based on GCC advice (vote at Jan 15 Council Mtg). See 'gateways' below)
|  | Contact Glos Police to request speed checks in village | _ | 2015-10-01 | OPEN | 2014-08-08 | After speed sign has been operative for a few months
FOOTPATHS | Create footway from Royal Oak to Littleworth turning | Contact Roger Wilson/Glos Highways regarding funding opportunities | 2014-10-01 | _ | CLOSED | 2015-03-12 | Advised by the Clerk that this work cannot be instigated by Parish Council. Closed.
| Improve footway from Manor Field to Royal Oak | Contact Roger Wilson/Glos Highways regarding funding opportunities | 2014-10-01 | 2015-08-01 | OPEN | 12/03/2015 14/5/2015 9/7/2015 | The Clerk will write to TBC asking for help. Roger Wilson advised that there may be money available at his discretion - clerk to write to him. Awaiting response from R Wilson
| Ensure footways are kept free of obstruction | Write to householders/landowners re their responsibilities | 2014-10-01 | 2015-09-01 | OPEN | 12/03/2015 9/7/2015 | Action amended. Clerk to write an article for inclusion in next GVA newsletter. Awaiting publication of next newsletter
DRAINAGE | Alleviate overflowing drains at Gopshill corner | Engage Glos Highways/Amey via Roger Wilson as previous works have not been effective | 2014-09-01 | 2015-01-01 | COMPLETE | 2015-03-12 | Work has been completed and appears successful.
| Alleviate overflowing drains near Gotherington turn. | Engage Glos Highways/Amey | 2015-09-01 | - | OPEN | 12/03/2015 9/7/2015 | Item added at March 15 Council Mtg. GCC & Amey engaged to rectify.
| Ensure ditches and culverts are kept clear | Write to householders/landowners re their responsibilities | 2014-10-01 | 2015-04-01 | COMPLETE | 12/03/2015 14/04/2015 9/7/2015 | Leaflets from TBC on Riparian Owner responsibilities to be delivered to houses with ditches etc. by PM & PA. Some leaflets delivered - awaiting more copies More leaflets distributed
APPEARANCE | Investigate feasibility of renovating and maintaining the Green & Triangle | Obtain quotes for periodic maintenance Assess condition of Oak Tree | _ | 2015-04-01 | COMPLETE | 12/03/2015 14/04/2015 14/05/2015 | PM & PA to assess the possibilities. Cut grass and plant flowers in centre recommended - for discussion at next mtg. Agreed to engage local gardener to cut grass only.
| Improve appearance of bus shelter and telephone box. | Inspect condition and make recommendation | 2014-09-01 | _ | COMPLETE | 01/09/2014 9/7/2015 | Bus shelter Inspected and found to be in acceptable condition. Telephone Box purchased by Council
| Improve appearance of village 'gateways' | Inspect white fences and 'hedgehog signs' and make recommendation. | 2014-09-01 | _ | UPDATED (see revised action below) | 11/09/2014 12/3/2015 | Signs are in good condition. Gateway is in very poor condition, but will remain in place until enquiries are completed regarding 'ownership' (11/09/14). GPC appears to own the Gateway, but this will remain in place until after David Rake has completed his study (see below).
| Produce a recommendation for Village Gateways (or not) in Gretton | Undertake a review of possible options and make a recommendation. | 2015-05-01 | 2015-11-01 | OPEN | 12/03/2015 9/7/2015 | David Rake has volunteered to undertake a study into possible 'Village Gateways' and report back at May 15 Mtg. Effectiveness in other villages to be investigated. Decision on implementation to be made before 2016 budget is set.
| Improve structural integrity and appearance of Chapel of Ease. | Establish ownership, and encourage proper maintenance. | End 2014 | 2015-09-01 | OPEN | 12/03/2015 9/7/2015 | MH to contact Church Council J Hurley now responsible for taking this forward
[6 empty] | 2015-09-10 | Trust to be formed independent of Parish Council
BROADBAND | Improve broadband provision in Gretton | Maintain pressure for upgrades. Monitor progress and report. |  | Ongoing | OPEN | 12/03/2015 9/7/2015 | Lastest information on Fastershire website indicates that work could be complete by June 2015, with December 2015 cited as a 'no later than' date for minimum of 2Mb service. Winchcombe connections should be upgradeable by September 2015. Alderton exchange work should be complete by end 2015.